## Task_Data
ID | % Complete | Task_Name | Duration | Predecessors
1 | 100% | Body Sheetmetal repair | 30
2 | 100% | Body patches | 10
3 | 100% | Door repair | 1 day?
4 | 100% | Cowl repair | 2 days
5 | 100% | Fender Patches | 9.5 days
6 | 100% | Subframe connector | 2 days?
7 | 100% | Floor pan prep | 2 days?
8 | 100% | Wheel Test | 1 day?
9 | 100% | Bumper repair | 1 day?
10 | 100% | Body Paint | 12.38 days? | 1
11 | 100% | Undercoating | 2 days?
12 | 50% | Dash prep | 1 day? | 11
13 | 100% | Final prep | 4.5 days | 12
14 | 100% | Sealer | 1.13 days | 13
15 | 100% | Base coat | 1 day? | 14
16 | 100% | Clear coat | 1 day? | 15
17 | 0% | Suspension |  | 10
18 | 0% | Front Suspension
19 | 0% | Steering
20 | 0% | Center link, Tie rod ends, Drag link
21 | 0% | Steering box (Rebuild)
22 | 0% | Steering Column (Rebuild)
23 | 0% | Steering Wheel
24 | 0% | Turn Signal and Horn Switches
25 | 0% | Rear Suspension
26 | 0% | Brakes
27 | 0% | Install Front Bearings
28 | 0% | Install Rotors |  | 27
29 | 0% | Install Hard Lines
30 | 0% | Install Soft Lines
31 | 0% | Master Cylinder/Booster |  | 30
32 | 0% | Install Brake pedal assembly |  | 31
33 | 0% | Emergency Brake Cables and connectors
34 | 0% | Emergency Brake Pedal assembly |  | 33
35 | 0% | DriveTrain |  | 10
36 | 0% | Engine
37 | 0% | Disassemble Engine and clean
38 | 0% | Paint |  | 37
39 | 0% | Rotating assembly with new bearings |  | 38
40 | 0% | Timing chain and gears |  | 39
41 | 0% | Oil Pump |  | 40
42 | 0% | Pan with Oil Pump Pickup |  | 41
43 | 0% | Heads and Gasket |  | 42
44 | 0% | Lifters, Pushrods, Rockers |  | 43
45 | 0% | Intake Manifold and gasket |  | 44
46 | 0% | Distributor |  | 45
47 | 0% | Fuel Lines, Fuel Pump |  | 46
48 | 0% | Wiring Harness |  | 47
49 | 0% | Computer, Sensors |  | 48
50 | 0% | Exhaust headers |  | 49
51 | 0% | Transmission |  | 50
52 | 0% | Plug holes and power wash
53 | 0% | Shift Kit Install |  | 52
54 | 0% | Transmission Mount
55 | 0% | Torque Converter
56 | 0% | Motor Mounts |  | 51
57 | 0% | Install Engine and Transmission in one unit |  | 36,56,51
58 | 0% | Transmission cooler and Lines
59 | 0% | Driveshaft |  | 51
60 | 0% | Rear Transmission |  | 59
61 | 0% | Exhaust Pipes and hangers |  | 57
62 | 0% | Wheels and Tires |  | 28,60
63 | 0% | Interior Trim |  | 35
64 | 0% | Electrical wiring harness
65 | 0% | Dash assembly |  | 64
66 | 0% | Carpeting |  | 64
67 | 0% | Center Console |  | 66
68 | 0% | Headliner |  | 64
69 | 0% | Plastic Trim |  | 68,66
70 | 0% | Seats |  | 69
71 | 0% | Exterior Trim |  | 63
72 | 0% | Door mechanical
73 | 0% | Windows |  | 72
74 | 0% | Lighting
75 | 0% | Body Trim |  | 73,74